## Summary Report
Summary report
Last Updated Date:- |  | 2025-03-31
Sr. No. | Region Name | Total Number of Scheme | No. of Functional Scheme | No. of Partial Scheme | No. of Fully Completed Scheme | Total Number of ESR | Number of Fully Completed ESR | Balance to Complete ESR
1 | Amravati | 15 | 1 | 14 | 1 | 695 | 66 | 629
2 | Nashik | 14 | 0 | 14 | 0 | 308 | 30 | 278
3 | Nagpur | 15 | 9 | 6 | 3 | 156 | 65 | 91
4 | Chhatrapati Sambhajinagar | 12 | 5 | 7 | 2 | 165 | 82 | 83
5 | Pune | 9 | 9 | 0 | 0 | 97 | 34 | 63
6 | Konkan | 4 | 3 | 1 | 0 | 13 | 3 | 10
Total |  | 69 | 27 | 42 | 6 | 1434 | 280 | 1154
Remarks
|  | Functional (Scheme) | If all village is Functional
|  | Partial (Scheme) | Few village is Functional
|  | No. Fully Completed Scheme | All theVillage and ESR is active as well as all the sensors are communicting with the system

## Region - Amravati Data (hidden)
[16 empty] | 200 | \\WIN-6SIR0BN8BTR\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Buldhana\Sub Division-Buldhana\Block-Buldhana\Scheme-20021406 - Padali & 5 Villages RRWSS\Padli
Region Wise Village Level Progress Report | [15 empty] | 9
30
161
Scheme Level
Sr No. | Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | Number of Village | No. of Functional Village | No. of Partial Village | No. of Non- Functional Village | Total Number of ESR | Scheme Functional Status | No. Fully Completed ESR | Balance ESR | Fully completion Scheme Status
1 | Amravati | Amravati | Achalpur | Chandur Bazar | 7945938 | 83 Village RRWS Scheme MJP RR (C 39) | 30 | 9 | 8 | 13 | 63 | Partial | 17 | 46 | In Progress
2 | Amravati | Yavatmal | Pusad | Pusad | 20028563 | Malpathar 28 Villages, (Reju.) | 30 | 2 | 7 | 21 | 62 | Partial | 0 | 62 | In Progress
3 | Amravati | Amravati W.M | W.M.Amravati - 2 | Achalpur | 20003791 | 105 Villages RRWSS | 10 | 2 | 5 | 3 | 20 | Partial | 0 | 20 | In Progress
4 | Amravati | Amravati W.M | W.M.Amravati - 2 | Amravati | 20003791 | 105 Villages RRWSS | 21 | 3 | 7 | 11 | 53 | Partial | 6 | 47 | In Progress
5 | Akola | Akola | Akola | Akola | 20028565 | Akot 84 VRRWSS Tq. Akola, Akot & Telhara Dist. Akola | 74 | 12 | 5 | 57 | 117 | Partial | 0 | 117 | In Progress
6 | Amravati | Amravati W.M | W.M.Amravati - 2 | Bhatkuli | 20003791 | 105 Villages RRWSS | 58 | 11 | 10 | 37 | 105 | Partial | 6 | 99 | In Progress
7 | Akola | Akola | Murtizapur | Murtizapur | 20028330 | Langhapur 50 VRRWSS Tq. Murtizapur Dist. Akola | 52 | 1 | 0 | 51 | 70 | Partial | 0 | 70 | In Progress
8 | Amravati | Amravati W.M | W.M.Amravati - 2 | Chandur Bazar | 20003791 | 105 Villages RRWSS | 25 | 7 | 4 | 14 | 53 | Partial | 4 | 49 | In Progress
9 | Amravati | Amravati | Amravati - 2 | Nandgaon Khandeshwar | 20030287 | Takli & 4 Villages RRWS | 5 | 4 | 1 | 0 | 8 | Partial | 0 | 8 | In Progress
10 | Akola | Buldhana | Buldhana | Motala | 20028065 | Pophali & 3 Villages RRWSS | 4 | 3 | 1 | 0 | 8 | Partial | 5 | 3 | In Progress
11 | Akola | Buldhana | Buldhana | Motala | 20021409 | Kurha & 2 Villages RRWSS | 3 | 2 | 0 | 1 | 4 | Partial | 1 | 3 | In Progress
12 | Akola | Buldhana | Buldhana | Motala | 20027978 | Dhamangaon Deshmukh & 9 Villages RRWSS | 10 | 8 | 2 | 0 | 17 | Partial | 10 | 7 | In Progress
13 | Akola | Buldhana | Buldhana | Buldhana | 20021406 | Padali & 5 Villages RRWSS | 6 | 6 | 0 | 0 | 7 | Functional | 7 | 0 | Completed
14 | Amravati | Amravati | Achalpur | Achalpur | 20029998 | Shahanur & 9 Villages RRWS | 10 | 4 | 3 | 3 | 15 | Partial | 3 | 12 | In Progress
15 | Amravati | Amravati | Achalpur | Achalpur | 7945938 | 83 Village RRWS Scheme MJP RR (C 39) | 58 | 3 | 6 | 49 | 93 | Partial | 7 | 86 | In Progress

## Amravati Datalink (hidden)
| Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | Number of Village | Calc - Village Functional | Calc - Village Partial | Calc - Village Non Functional | Calc - Scheme Status | Number of the Reservoir
\\DemoAF\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Amravati\Division-Amravati\Sub Division-Achalpur\Block-Chandur Bazar\Scheme-7945938 - 83 Village RRWS Scheme MJP RR (C 39) | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Amravati\Division-Yavatmal\Sub Division-Pusad\Block-Pusad\Scheme-20028563 - Malpathar 28 villages, (Reju.) | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Amravati\Division-Amravati W.M\Sub Division-W.M.Amravati - 2\Block-Achalpur\Scheme-20003791 - 105 villages RRWSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Amravati\Division-Amravati W.M\Sub Division-W.M.Amravati - 2\Block-Amravati\Scheme-20003791 - 105 villages RRWSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Akola\Sub Division-Akola\Block-Akola\Scheme-20028565 - Akot 84 VRRWSS Tq. Akola, Akot & Telhara Dist. Akola | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Amravati\Division-Amravati W.M\Sub Division-W.M.Amravati - 2\Block-Bhatkuli\Scheme-20003791 - 105 villages RRWSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Akola\Sub Division-Murtizapur\Block-Murtizapur\Scheme-20028330 - Langhapur 50 VRRWSS Tq. Murtizapur Dist. Akola | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Amravati\Division-Amravati W.M\Sub Division-W.M.Amravati - 2\Block-Chandur Bazar\Scheme-20003791 - 105 villages RRWSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Amravati\Division-Amravati\Sub Division-Amravati - 2\Block-Nandgaon Khandeshwar\Scheme-20030287 - Takli & 4 Villages RRWS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Buldhana\Sub Division-Buldhana\Block-Motala\Scheme-20028065 - Pophali & 3 Villages RRWSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Buldhana\Sub Division-Buldhana\Block-Motala\Scheme-20021409 - Kurha & 2 Villages RRWSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Buldhana\Sub Division-Buldhana\Block-Motala\Scheme-20027978 - Dhamangaon Deshmukh & 9 Villages RRWSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Buldhana\Sub Division-Buldhana\Block-Buldhana\Scheme-20021406 - Padali & 5 Villages RRWSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Amravati\Division-Amravati\Sub Division-Achalpur\Block-Achalpur\Scheme-20029998 - Shahanur & 9 Villages RRWS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Amravati\Division-Amravati\Sub Division-Achalpur\Block-Achalpur\Scheme-7945938 - 83 Village RRWS Scheme MJP RR (C 39) | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?

## Region - Amravati
\\WIN-6SIR0BN8BTR\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Buldhana\Sub Division-Buldhana\Block-Buldhana\Scheme-20021406 - Padali & 5 Villages RRWSS\Padli
Region Wise Village Level Progress Report
Scheme Level
[6 empty] | Total Number of Scheme | No. of Functional Scheme | No. of Partial Scheme | No. of Fully Completed Scheme | Total Number of ESR | Number of Fully Completed ESR | Balance to Complete ESR | [6 empty] | Remarks
[6 empty] | 15 | 1 | 14 | 1 | 695 | 66 | 629 | [6 empty] | No. of Functional Village | All ESR is active
|  | 0 | [16 empty] | No. of Partial Village | Few ESR is active
Sr No. | Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | No. of Village | No. of Functional Village | No. of Partial Village | No. of Non- Functional Village | Total Number of ESR | Scheme Functional Status | No. Fully Completed ESR | Balance to Complete ESR | Flow Meters Conneted | Pressure Transmitter Conneted | Residual Chlorine Conneted | Scheme Status | No. of Non- Functional Village | None of the ESR is active
1 | Amravati | Amravati | Achalpur | Chandur Bazar | 7945938 | 83 Village RRWS Scheme MJP RR (C 39) | 30 | 9 | 8 | 13 | 63 | Partial | 17 | 46 | 27 | 24 | 27 | In Progress | Functional (Scheme) | If all village is Functional
2 | Amravati | Yavatmal | Pusad | Pusad | 20028563 | Malpathar 28 Villages, (Reju.) | 30 | 2 | 7 | 21 | 62 | Partial | 0 | 62 | 8 | 10 | 0 | In Progress | Partial (Scheme) | Few village is Functional
3 | Amravati | Amravati W.M | W.M.Amravati - 2 | Achalpur | 20003791 | 105 Villages RRWSS | 10 | 2 | 5 | 3 | 20 | Partial | 0 | 20 | 66 | 55 | 24 | In Progress | No. Fully Completed ESR | All the ESR is active as well as all the sensors are communicting with the system
5 | Akola | Akola | Akola | Akola | 20028565 | Akot 84 VRRWSS Tq. Akola, Akot & Telhara Dist. Akola | 74 | 12 | 5 | 57 | 117 | Partial | 0 | 117 | 4 | 0 | 4 | In Progress | In Progress | Any village is partial (some ESR is active,Some sensor is active)
7 | Akola | Akola | Murtizapur | Murtizapur | 20028330 | Langhapur 50 VRRWSS Tq. Murtizapur Dist. Akola | 52 | 1 | 0 | 51 | 70 | Partial | 0 | 70 | 1 | 1 | 0 | In Progress
9 | Amravati | Amravati | Amravati - 2 | Nandgaon Khandeshwar | 20030287 | Takli & 4 Villages RRWS | 5 | 4 | 1 | 0 | 8 | Partial | 0 | 8 | 7 | 2 | 3 | In Progress
10 | Akola | Buldhana | Buldhana | Motala | 20028065 | Pophali & 3 Villages RRWSS | 4 | 3 | 1 | 0 | 8 | Partial | 5 | 3 | 7 | 5 | 6 | In Progress
11 | Akola | Buldhana | Buldhana | Motala | 20021409 | Kurha & 2 Villages RRWSS | 3 | 2 | 0 | 1 | 4 | Partial | 1 | 3 | 3 | 1 | 3 | In Progress
12 | Akola | Buldhana | Buldhana | Motala | 20027978 | Dhamangaon Deshmukh & 9 Villages RRWSS | 10 | 8 | 2 | 0 | 17 | Partial | 10 | 7 | 15 | 8 | 13 | In Progress
13 | Akola | Buldhana | Buldhana | Buldhana | 20021406 | Padali & 5 Villages RRWSS | 6 | 6 | 0 | 0 | 7 | Functional | 7 | 0 | 7 | 7 | 7 | Completed
14 | Amravati | Amravati | Achalpur | Achalpur | 20029998 | Shahanur & 9 Villages RRWS | 10 | 4 | 3 | 3 | 15 | Partial | 3 | 12 | 6 | 6 | 6 | In Progress

## Region - Nashik
\\WIN-6SIR0BN8BTR\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Buldhana\Sub Division-Buldhana\Block-Buldhana\Scheme-20021406 - Padali & 5 Villages RRWSS\Padli
Region Wise Village Level Progress Report
Scheme Level
[6 empty] | Total Number of Scheme | No. of Functional Scheme | No. of Partial Scheme | No. of Fully Completed Scheme | Total Number of ESR | Number of Fully Completed ESR | Balance to Complete ESR | [6 empty] | Remarks
[6 empty] | 14 | 0 | 14 | 0 | 308 | 30 | 278 | [6 empty] | No. of Functional Village | All ESR is active
|  | 0 | [16 empty] | No. of Partial Village | Few ESR is active
Sr No. | Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | Number of Village | No. of Functional Village | No. of Partial Village | No. of Non- Functional Village | Total Number of ESR | Scheme Functional Status | No. Fully Completed ESR | Balance to Complete ESR | Flow Meters Conneted | Pressure Transmitter Conneted | Residual Chlorine Conneted | Fully completion Scheme Status | No. of Non- Functional Village | None of the ESR is active
1 | Nashik | W M Nashik | W.M.Nashik | Nifad | 20039258 | Ozar-Sakore & 2 Villages | 2 | 1 | 1 | 0 | 6 | Partial | 3 | 3 | 6 | 5 | 7 | In Progress | Functional (Scheme) | If all village is Functional
2 | Nashik | W M Nashik | Sinnar | Naigaon | 20028193 | Retrofitting To Wadzire (Naigaon) & 4 Villages RRWSS | 4 | 1 | 1 | 2 | 5 | Partial | 0 | 5 | 2 | 0 | 1 | In Progress | Partial (Scheme) | Few village is Functional
3 | Ahmednagar | Sangamner | Sangamner | Sangamner | 7937337 | Retro.Nimon and 4 villages, Tal. Sangamner | 6 | 2 | 3 | 1 | 19 | Partial | 7 | 12 | 11 | 7 | 7 | In Progress | No. Fully Completed ESR | All the ESR is active as well as all the sensors are communicting with the system
4 | Ahmednagar | Sangamner | Sangamner | Sangamner | 20033242 | Retro.Talegaon Dighe and 16 villages, Tal. Sangamner | 20 | 3 | 1 | 16 | 50 | Partial | 4 | 46 | 6 | 4 | 6 | In Progress | Completed | All ESR is active as well as all sensor is active.
5 | Nashik | W M Nashik | Malegaon | Chandwad | 20086730 | Retro.Chandwad and WSS 44 villages. Ta. Chandwad | 58 | 16 | 2 | 40 | 75 | Partial | 0 | 75 | 5 | 6 | 10 | In Progress | In Progress | Any village is partial (some ESR is active,Some sensor is active)
6 | Ahmednagar | Sangamner | Kopargaon | Rahata | 20054877 | Retro.Kelvad Bk.& 2 villages RRWSS. Ta.Rahta | 3 | 1 | 1 | 1 | 5 | Partial | 0 | 5 | 2 | 0 | 2 | In Progress
7 | Ahmednagar | Sangamner | Kopargaon | Rahata | 417239 | Retro Rui & Shingave R.R.W.S.S Tal Rahata | 2 | 1 | 1 | 0 | 7 | Partial | 4 | 3 | 6 | 4 | 5 | Completed
8 | Jalgaon | Jalgaon | Erandol | Dharangaon | 20061165 | Paldhi (bk& Kh) RR Tal DHARANGAON | 2 | 1 | 1 | 0 | 6 | Partial | 5 | 1 | 5 | 5 | 5 | In Progress
10 | Nashik | Nashik | Sinnar | Sinnar | 20019176 | Retro. Bargaonpimpri & 6 VRWSS Tal Sinnar | 7 | 4 | 1 | 2 | 16 | Partial | 5 | 11 | 8 | 5 | 12 | In Progress
11 | Nashik | Nashik | Sinnar | Sinnar | 20019286 | Nirhale-Fatehpur and 5 villages, Tal. Sinnar | 5 | 2 | 1 | 2 | 11 | Partial | 0 | 11 | 8 | 2 | 2 | In Progress
12 | Nashik | Nashik | Manmad | Yeola | 20030798 | Retrofitting To Yeola 38 Villages | 28 | 17 | 0 | 11 | 33 | Partial | 0 | 33 | 9 | 0 | 13 | In Progress
13 | Jalgaon | Jalgaon | Erandol | Chalisgaon | 20053796 | Dondigar-Rohini & 15 Villages WSS | 17 | 1 | 1 | 15 | 35 | Partial | 0 | 35 | 1 | 2 | 1 | In Progress
14 | Ahmednagar | Ahmednagar | Newasa | Nevasa | 5348540 | Retro.Sonai Karjgaon and 16 villages, Tal. Nevasa | 18 | 3 | 11 | 4 | 36 | Partial | 0 | 36 | 13 | 0 | 12 | In Progress

## Region - Nagpur
\\WIN-6SIR0BN8BTR\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Buldhana\Sub Division-Buldhana\Block-Buldhana\Scheme-20021406 - Padali & 5 Villages RRWSS\Padli
Region Wise Village Level Progress Report
Scheme Level
[6 empty] | Total Number of Scheme | No. of Functional Scheme | No. of Partial Scheme | No. of Fully Completed Scheme | Total Number of ESR | Number of Fully Completed ESR | Balance to Complete ESR | [6 empty] | Remarks
[6 empty] | 15 | 9 | 6 | 3 | 156 | 65 | 91 | [6 empty] | No. of Functional Village | All ESR is active
|  | 36 | [16 empty] | No. of Partial Village | Few ESR is active
Sr No. | Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | Number of Village | No. of Functional Village | No. of Partial Village | No. of Non- Functional Village | Total Number of ESR | Scheme Functional Status | No. Fully Completed ESR | Balance to Complete ESR | Flow Meters Conneted | Pressure Transmitter Conneted | Residual Chlorine Conneted | Fully completion Scheme Status | No. of Non- Functional Village | None of the ESR is active
1 | Nagpur | Chandrapur | Chandrapur | Chimur | 20036536 | Bothali & 7 Village RR WSS | 8 | 8 | 0 | 0 | 8 | Functional | 6 | 2 | 8 | 6 | 8 | In Progress | Functional (Scheme) | If all village is Functional
2 | Nagpur | Chandrapur | Gadchiroli | Chamorshi | 2009882 | Ghot RRWSS | 3 | 3 | 0 | 0 | 4 | Functional | 3 | 1 | 4 | 3 | 4 | In Progress | Partial (Scheme) | Few village is Functional
3 | Chandrapur | Chandrapur | Chandrapur | Chandrapur | 20050368 | Chinchala and 7 Villages RR Water Supply Scheme | 8 | 1 | 7 | 0 | 17 | Partial | 2 | 15 | 9 | 2 | 8 | In Progress | No. Fully Completed ESR | All the ESR is active as well as all the sensors are communicting with the system
4 | Nagpur | Nagpur | Chandrapur | Saoali | 20036500 | Vyahad & 2 Village RR WSS | 3 | 2 | 1 | 0 | 5 | Partial | 1 | 4 | 4 | 1 | 4 | In Progress | Completed | All ESR is active as well as all sensor is active.
5 | Nagpur | Chandrapur | Wardha | Wardha | 7891298 | Pipri Meghe and 13 villages RR WSS | 13 | 6 | 4 | 3 | 23 | Partial | 11 | 12 | 14 | 12 | 14 | In Progress | In Progress | Any village is partial (some ESR is active,Some sensor is active)
6 | Chandrapur | Chandrapur | Pombhurna | Pombhurna | 7928270 | Pomnbhurna Grid & 15 Villages RR Retrofitting | 18 | 14 | 1 | 3 | 22 | Partial | 0 | 22 | 16 | 0 | 17 | In Progress
7 | Chandrapur | Chandrapur | Gadchiroli | Aheri | 7890975 | Allapalli-Nagapalli RR | 2 | 2 | 0 | 0 | 2 | Functional | 2 | 0 | 2 | 2 | 2 | Completed
8 | Nagpur | Gondia | Gondia | Goregaon | 20019216 | GOREGAON RR Retrofitting | 5 | 5 | 0 | 0 | 7 | Functional | 5 | 2 | 7 | 5 | 7 | In Progress
9 | Nagpur | Chandrapur | Mul | Mul | 7890965 | Mul Grid & 24 Villages RR WSS Retrofitting | 25 | 11 | 1 | 13 | 28 | Partial | 0 | 28 | 11 | 0 | 12 | In Progress
10 | Nagpur | Nagpur | Nagpur | Hingna | 20009650 | Waddhmna WSS | 2 | 2 | 0 | 0 | 7 | Functional | 7 | 0 | 7 | 7 | 7 | Completed
11 | Nagpur | Gondia | Gondia | Gondia | 2003645 | Kudwa-Katangikala Peri Urban RR | 2 | 2 | 0 | 0 | 5 | Functional | 4 | 1 | 5 | 4 | 5 | In Progress
12 | Nagpur | Gondia | Bhandara | Tumsar | 631010 | Gobarwahi RR Retrofitting | 9 | 9 | 0 | 0 | 11 | Functional | 9 | 2 | 11 | 9 | 10 | In Progress
13 | Nagpur | Gondia | Bhandara | Tumsar | 20017217 | Dewadi RR WSS | 6 | 6 | 0 | 0 | 7 | Functional | 6 | 1 | 7 | 6 | 7 | In Progress
14 | Nagpur | Nagpur | Nagpur | Kamptee | 7940695 | Bidgaon Tarodi wss | 2 | 2 | 0 | 0 | 4 | Functional | 4 | 0 | 4 | 4 | 4 | Completed
15 | Nagpur | Chandrapur | Chandrapur | Mul | 20036862 | Bor Chandli 5 Village RR WSS | 6 | 5 | 0 | 1 | 6 | Partial | 5 | 1 | 5 | 5 | 5 | In Progress

## Nagpur Datalink (hidden)
| Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | Number of Village | Calc - Village Functional | Calc - Village Partial | Calc - Village Non Functional | Calc - Scheme Status | Number of the Reservoir
\\DemoAF\JJM\JJM\Maharashtra\Region-Nagpur\Circle-Nagpur\Division-Chandrapur\Sub Division-Chandrapur\Block-Chimur\Scheme-20036536 - Bothali & 7 Village RR WSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nagpur\Circle-Nagpur\Division-Chandrapur\Sub Division-Gadchiroli\Block-Chamorshi\Scheme-2009882 - Ghot Rrwss | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nagpur\Circle-Chandrapur\Division-Chandrapur\Sub Division-Chandrapur\Block-Chandrapur\Scheme-20050368 - Chinchala and 7 Villages RR Water Supply Scheme | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nagpur\Circle-Nagpur\Division-Nagpur\Sub Division-Chandrapur\Block-Saoali\Scheme-20036500 - Vyahad & 2 Village Rr Wss | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nagpur\Circle-Nagpur\Division-Chandrapur\Sub Division-Wardha\Block-Wardha\Scheme-7891298 - Pipri Meghe and 13 villages RR WSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nagpur\Circle-Chandrapur\Division-Chandrapur\Sub Division-Pombhurna\Block-Pombhurna\Scheme-7928270 - Pomnbhurna Grid & 15 Villages RR Retrofitting | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nagpur\Circle-Chandrapur\Division-Chandrapur\Sub Division-Gadchiroli\Block-Aheri\Scheme-7890975 - Allapalli-Nagapalli RR | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nagpur\Circle-Nagpur\Division-Gondia\Sub Division-Gondia\Block-Goregaon\Scheme-20019216 - GOREGAON RR Retrofitting | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nagpur\Circle-Nagpur\Division-Chandrapur\Sub Division-Mul\Block-Mul\Scheme-7890965 - Mul Grid & 24 Villages RR WSS Retrofitting | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nagpur\Circle-Nagpur\Division-Nagpur\Sub Division-Nagpur\Block-Hingna\Scheme-20009650 - Waddhmna WSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nagpur\Circle-Nagpur\Division-Gondia\Sub Division-Gondia\Block-Gondia\Scheme-2003645 - Kudwa-Katangikala Peri Urban RR | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nagpur\Circle-Nagpur\Division-Gondia\Sub Division-Bhandara\Block-Tumsar\Scheme-631010 - Gobarwahi RR Retrofitting | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nagpur\Circle-Nagpur\Division-Gondia\Sub Division-Bhandara\Block-Tumsar\Scheme-20017217 - Dewadi RR WSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nagpur\Circle-Nagpur\Division-Nagpur\Sub Division-Nagpur\Block-Kamptee\Scheme-7940695 - Bidgaon Tarodi wss | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nagpur\Circle-Nagpur\Division-Chandrapur\Sub Division-Chandrapur\Block-Mul\Scheme-20036862 - Bor Chandli 5 Village RR WSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?

## Region - Konkan Data (hidden)
[16 empty] | 200 | \\WIN-6SIR0BN8BTR\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Buldhana\Sub Division-Buldhana\Block-Buldhana\Scheme-20021406 - Padali & 5 Villages RRWSS\Padli
Region Wise Village Level Progress Report | [15 empty] | 9
30
161
Scheme Level
Sr No. | Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | Number of Village | No. of Functional Village | No. of Partial Village | No. of Non- Functional Village | Total Number of ESR | Scheme Functional Status | No. Fully Completed ESR | Balance ESR | Fully completion Scheme Status
1 | Panvel | Raigadh | Mangaon | Khalapur | 20028168 | Devnhave water supply scheme | 1 | 0 | 1 | 0 | 3 | Partial | 0 | 3 | In Progress
2 | Panvel | Raigadh | Mangaon | Pen | 20020563 | Shahapada 38 Villages | 5 | 5 | 0 | 0 | 5 | Functional | 3 | 2 | In Progress
3 | Thane | Thane | Palghar | Dahanu | 20047871 | Modgaon & Tornipada RWSS | 4 | 4 | 0 | 0 | 4 | Functional | 0 | 4 | In Progress
4 | Thane | Thane | Thane | Kalyan | 20092478 | Retrofiting of Gotheghar Dahisar R.R. Water Supply Scheme | 1 | 1 | 0 | 0 | 1 | Functional | 0 | 1 | In Progress
0
0
0
0

## Konkan Datalink (hidden)
| Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | Number of Village | Calc - Village Functional | Calc - Village Partial | Calc - Village Non Functional | Calc - Scheme Status | Number of the Reservoir
\\DemoAF\JJM\JJM\Maharashtra\Region-Konkan\Circle-Panvel\Division-Raigadh\Sub Division-Mangaon\Block-Khalapur\Scheme-20028168 - Devnhave water supply scheme | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Konkan\Circle-Panvel\Division-Raigadh\Sub Division-Mangaon\Block-Pen\Scheme-20020563-Shahapada 38 Villages | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Konkan\Circle-Thane\Division-Thane\Sub Division-Palghar\Block-Dahanu\Scheme-20047871-Modgaon & Tornipada RWSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Konkan\Circle-Thane\Division-Thane\Sub Division-Thane\Block-Kalyan\Scheme-20092478-Retrofiting of Gotheghar Dahisar R.R. Water Supply Scheme | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?

## Region - CS
\\WIN-6SIR0BN8BTR\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Buldhana\Sub Division-Buldhana\Block-Buldhana\Scheme-20021406 - Padali & 5 Villages RRWSS\Padli
Region Wise Village Level Progress Report
Scheme Level
[6 empty] | Total Number of Scheme | No. of Functional Scheme | No. of Partial Scheme | No. of Fully Completed Scheme | Total Number of ESR | Number of Fully Completed ESR | Balance to Complete ESR | [6 empty] | Remarks
[6 empty] | 12 | 5 | 7 | 2 | 165 | 82 | 83 | [6 empty] | No. of Functional Village | All ESR is active
|  | 0 | [16 empty] | No. of Partial Village | Few ESR is active
Sr No. | Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | Number of Village | No. of Functional Village | No. of Partial Village | No. of Non- Functional Village | Total Number of ESR | Scheme Functional Status | No. Fully Completed ESR | Balance to Complete ESR | Flow Meters Conneted | Pressure Transmitter Conneted | Residual Chlorine Conneted | Fully completion Scheme Status | No. of Non- Functional Village | None of the ESR is active
1 | Latur | Latur | Chakur | Chakur | 20030459 | Rachnawadi 6 villages WSS | 2 | 2 | 0 | 0 | 2 | Functional | 2 | 0 | 2 | 2 | 2 | Completed | Functional (Scheme) | If all village is Functional
2 | Chhatrapati Sambhajinagar | Chhatrapati Sambhajinagar | Paithan | Paithan | 20018162 | Paithan Taluka 178 Village Grid WS | 44 | 43 | 0 | 1 | 45 | Partial | 38 | 7 | 44 | 38 | 44 | In Progress | Partial (Scheme) | Few village is Functional
3 | Chhatrapati Sambhajinagar | Chhatrapati Sambhajinagar | Gangapur | Gangapur | 20051233 | 373 Village Gangapur-Vaijapur Grid WSS | 7 | 5 | 0 | 2 | 7 | Partial | 2 | 5 | 35 | 27 | 36 | In Progress | No. Fully Completed ESR | All the ESR is active as well as all the sensors are communicting with the system
4 | Chhatrapati Sambhajinagar | Chhatrapati Sambhajinagar | Sillod | Sillod | 20017395 | Shirsala & 4 Village | 4 | 3 | 0 | 1 | 5 | Partial | 2 | 3 | 4 | 2 | 4 | In Progress | Completed | All ESR is active as well as all sensor is active.
5 | Nanded | Nanded | Himayatnagar | Himayatnagar | 20013969 | Hadgaon and Himayatnagar 132 Village Grid WSS | 9 | 7 | 1 | 1 | 9 | Partial | 1 | 8 | 32 | 19 | 36 | In Progress | In Progress | Any village is partial (some ESR is active,Some sensor is active)
6 | Nanded | Nanded | Naigaon | Naigaon | 7942142 | Manjram WSS (7942142) | 2 | 2 | 0 | 0 | 2 | Functional | 2 | 0 | 2 | 2 | 2 | Completed
7 | Nanded | Parbhani | Senaon | Senaon | 20023330 | Kawtha Bk & 9 Vill RR WSS | 1 | 1 | 0 | 0 | 1 | Functional | 0 | 1 | 1 | 0 | 1 | In Progress
8 | Latur | Latur | Renapur | Renapur | 20030820 | Pangaon 10 villages WSS | 4 | 4 | 0 | 0 | 5 | Functional | 0 | 5 | 3 | 0 | 4 | In Progress
9 | Latur | Latur | Shirur Anantpal | Shirur Anantpal | 20030815 | Sakol 7 villages WSS | 3 | 2 | 1 | 0 | 4 | Partial | 3 | 1 | 4 | 3 | 3 | In Progress
10 | Nanded | Nanded | Kandhar | Kandhar | 7338000 | Osmamnagar Shirdhon Combined WSS | 4 | 4 | 0 | 0 | 7 | Functional | 0 | 7 | 6 | 0 | 7 | In Progress

## Region - Pune
\\WIN-6SIR0BN8BTR\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Buldhana\Sub Division-Buldhana\Block-Buldhana\Scheme-20021406 - Padali & 5 Villages RRWSS\Padli
Region Wise Village Level Progress Report
Scheme Level
[6 empty] | Total Number of Scheme | No. of Functional Scheme | No. of Partial Scheme | No. of Fully Completed Scheme | Total Number of ESR | Number of Fully Completed ESR | Balance to Complete ESR | [6 empty] | Remarks
[6 empty] | 9 | 9 | 0 | 0 | 97 | 34 | 63 | [6 empty] | No. of Functional Village | All ESR is active
|  | 0 | [16 empty] | No. of Partial Village | Few ESR is active
Sr No. | Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | Number of Village | No. of Functional Village | No. of Partial Village | No. of Non- Functional Village | Total Number of ESR | Scheme Functional Status | No. Fully Completed ESR | Balance to Complete ESR | Flow Meters Conneted | Pressure Transmitter Conneted | Residual Chlorine Conneted | Fully completion Scheme Status | No. of Non- Functional Village | None of the ESR is active
1 | Pune | Pune 2 | Pune 2 | Velhe | 20027541 | Wangani RRWSS | 4 | 4 | 0 | 0 | 6 | Functional | 0 | 6 | 6 | 0 | 4 | In Progress | Functional (Scheme) | If all village is Functional
2 | Pune | Satara | Phaltan | Phaltan | 20027892 | RR Girvi WSS | 5 | 5 | 0 | 0 | 5 | Functional | 2 | 3 | 5 | 2 | 5 | In Progress | Partial (Scheme) | Few village is Functional
3 | Pune | Pune 1 | Baramati | Ambegaon | 20017250 | LONI BHAPKAR RRWSS | 8 | 8 | 0 | 0 | 20 | Functional | 9 | 11 | 20 | 16 | 12 | In Progress | No. Fully Completed ESR | All the ESR is active as well as all the sensors are communicting with the system
4 | Pune | MJP Works Division No. 2 , Pune | Pune | Mulshi | 20022133 | Peth RR | 3 | 3 | 0 | 0 | 11 | Functional | 0 | 11 | 10 | 0 | 6 | In Progress | Completed | All ESR is active as well as all sensor is active.
5 | Pune | Pune 2 | Maval | Daund | 20013367 | Done Adhale RR | 4 | 4 | 0 | 0 | 7 | Functional | 3 | 4 | 7 | 3 | 5 | In Progress | In Progress | Any village is partial (some ESR is active,Some sensor is active)
6 | Sangli | Solapur | Solapur | Sangola | 20027396 | Alegaon shirbhavi 82 Village | 17 | 17 | 0 | 0 | 22 | Functional | 13 | 9 | 22 | 18 | 16 | In Progress
7 | Sangli | Sangli | Islampur | Valva | 7940233 | Peth & two Villages | 3 | 3 | 0 | 0 | 5 | Functional | 0 | 5 | 4 | 0 | 5 | In Progress
8 | Pune | Pune 1 | Baramati | Ambegaon | 7942125 | MURTI & 7 VILLAGES RRWSS | 7 | 7 | 0 | 0 | 13 | Functional | 4 | 9 | 13 | 8 | 5 | In Progress
9 | Pune | Pune 2 | Baramati | Ambegaon | 20018548 | HOL SASTEWADI | 2 | 2 | 0 | 0 | 8 | Functional | 3 | 5 | 8 | 3 | 7 | In Progress

## Region - Konkan
\\WIN-6SIR0BN8BTR\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Buldhana\Sub Division-Buldhana\Block-Buldhana\Scheme-20021406 - Padali & 5 Villages RRWSS\Padli
Region Wise Village Level Progress Report
Scheme Level
[6 empty] | Total Number of Scheme | No. of Functional Scheme | No. of Partial Scheme | No. of Fully Completed Scheme | Total Number of ESR | Number of Fully Completed ESR | Balance to Complete ESR | [6 empty] | Remarks
[6 empty] | 4 | 3 | 1 | 0 | 13 | 3 | 10 | [6 empty] | No. of Functional Village | All ESR is active
|  | 0 | [16 empty] | No. of Partial Village | Few ESR is active
Sr No. | Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | Number of Village | No. of Functional Village | No. of Partial Village | No. of Non- Functional Village | Total Number of ESR | Scheme Functional Status | No. Fully Completed ESR | Balance to Complete ESR | Flow Meters Conneted | Pressure Transmitter Conneted | Residual Chlorine Conneted | Fully completion Scheme Status | No. of Non- Functional Village | None of the ESR is active
1 | Panvel | Raigadh | Mangaon | Khalapur | 20028168 | Devnhave water supply scheme | 1 | 0 | 1 | 0 | 3 | Partial | 0 | 3 | 1 | 0 | 1 | In Progress | Functional (Scheme) | If all village is Functional
2 | Panvel | Raigadh | Mangaon | Pen | 20020563 | Shahapada 38 Villages | 5 | 5 | 0 | 0 | 5 | Functional | 3 | 2 | 5 | 3 | 5 | In Progress | Partial (Scheme) | Few village is Functional
3 | Thane | Thane | Palghar | Dahanu | 20047871 | Modgaon & Tornipada RWSS | 4 | 4 | 0 | 0 | 4 | Functional | 0 | 4 | 4 | 1 | 4 | In Progress | No. Fully Completed ESR | All the ESR is active as well as all the sensors are communicting with the system
4 | Thane | Thane | Thane | Kalyan | 20092478 | Retrofiting of Gotheghar Dahisar R.R. Water Supply Scheme | 1 | 1 | 0 | 0 | 1 | Functional | 0 | 1 | 1 | 0 | 0 | In Progress | Completed | All ESR is active as well as all sensor is active.
[19 empty] | In Progress | Any village is partial (some ESR is active,Some sensor is active)

## Region - Nagpur Data (hidden)
[16 empty] | 200 | \\WIN-6SIR0BN8BTR\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Buldhana\Sub Division-Buldhana\Block-Buldhana\Scheme-20021406 - Padali & 5 Villages RRWSS\Padli
Region Wise Village Level Progress Report | [15 empty] | 9
30
161
Scheme Level
Sr No. | Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | Number of Village | No. of Functional Village | No. of Partial Village | No. of Non- Functional Village | Total Number of ESR | Scheme Functional Status | No. Fully Completed ESR | Balance ESR | Fully completion Scheme Status
1 | Nagpur | Chandrapur | Chandrapur | Chimur | 20036536 | Bothali & 7 Village RR WSS | 8 | 8 | 0 | 0 | 8 | Functional | 6 | 2 | In Progress
2 | Nagpur | Chandrapur | Gadchiroli | Chamorshi | 2009882 | Ghot RRWSS | 3 | 3 | 0 | 0 | 4 | Functional | 3 | 1 | In Progress
3 | Chandrapur | Chandrapur | Chandrapur | Chandrapur | 20050368 | Chinchala and 7 Villages RR Water Supply Scheme | 8 | 1 | 7 | 0 | 17 | Partial | 2 | 15 | In Progress
4 | Nagpur | Nagpur | Chandrapur | Saoali | 20036500 | Vyahad & 2 Village RR WSS | 3 | 2 | 1 | 0 | 5 | Partial | 1 | 4 | In Progress
5 | Nagpur | Chandrapur | Wardha | Wardha | 7891298 | Pipri Meghe and 13 villages RR WSS | 13 | 6 | 4 | 3 | 23 | Partial | 11 | 12 | In Progress
6 | Chandrapur | Chandrapur | Pombhurna | Pombhurna | 7928270 | Pomnbhurna Grid & 15 Villages RR Retrofitting | 18 | 14 | 1 | 3 | 22 | Partial | 0 | 22 | In Progress
7 | Chandrapur | Chandrapur | Gadchiroli | Aheri | 7890975 | Allapalli-Nagapalli RR | 2 | 2 | 0 | 0 | 2 | Functional | 2 | 0 | Completed
8 | Nagpur | Gondia | Gondia | Goregaon | 20019216 | GOREGAON RR Retrofitting | 5 | 5 | 0 | 0 | 7 | Functional | 5 | 2 | In Progress
9 | Nagpur | Chandrapur | Mul | Mul | 7890965 | Mul Grid & 24 Villages RR WSS Retrofitting | 25 | 11 | 1 | 13 | 28 | Partial | 0 | 28 | In Progress
10 | Nagpur | Nagpur | Nagpur | Hingna | 20009650 | Waddhmna WSS | 2 | 2 | 0 | 0 | 7 | Functional | 7 | 0 | Completed
11 | Nagpur | Gondia | Gondia | Gondia | 2003645 | Kudwa-Katangikala Peri Urban RR | 2 | 2 | 0 | 0 | 5 | Functional | 4 | 1 | In Progress
12 | Nagpur | Gondia | Bhandara | Tumsar | 631010 | Gobarwahi RR Retrofitting | 9 | 9 | 0 | 0 | 11 | Functional | 9 | 2 | In Progress
13 | Nagpur | Gondia | Bhandara | Tumsar | 20017217 | Dewadi RR WSS | 6 | 6 | 0 | 0 | 7 | Functional | 6 | 1 | In Progress
14 | Nagpur | Nagpur | Nagpur | Kamptee | 7940695 | Bidgaon Tarodi wss | 2 | 2 | 0 | 0 | 4 | Functional | 4 | 0 | Completed
15 | Nagpur | Chandrapur | Chandrapur | Mul | 20036862 | Bor Chandli 5 Village RR WSS | 6 | 5 | 0 | 1 | 6 | Partial | 5 | 1 | In Progress

## Region - Pune Data (hidden)
[16 empty] | 200 | \\WIN-6SIR0BN8BTR\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Buldhana\Sub Division-Buldhana\Block-Buldhana\Scheme-20021406 - Padali & 5 Villages RRWSS\Padli
Region Wise Village Level Progress Report | [15 empty] | 9
30
161
Scheme Level
Sr No. | Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | Number of Village | No. of Functional Village | No. of Partial Village | No. of Non- Functional Village | Total Number of ESR | Scheme Functional Status | No. Fully Completed ESR | Balance ESR | Fully completion Scheme Status
1 | Pune | Pune 2 | Pune 2 | Velhe | 20027541 | Wangani RRWSS | 4 | 4 | 0 | 0 | 6 | Functional | 0 | 6 | In Progress
2 | Pune | Satara | Phaltan | Phaltan | 20027892 | RR Girvi WSS | 5 | 5 | 0 | 0 | 5 | Functional | 2 | 3 | In Progress
3 | Pune | Pune 1 | Baramati | Ambegaon | 20017250 | LONI BHAPKAR RRWSS | 8 | 8 | 0 | 0 | 20 | Functional | 9 | 11 | In Progress
4 | Pune | MJP Works Division No. 2 , Pune | Pune | Mulshi | 20022133 | Peth RR | 3 | 3 | 0 | 0 | 11 | Functional | 0 | 11 | In Progress
5 | Pune | Pune 2 | Maval | Daund | 20013367 | Done Adhale RR | 4 | 4 | 0 | 0 | 7 | Functional | 3 | 4 | In Progress
6 | Sangli | Solapur | Solapur | Sangola | 20027396 | Alegaon shirbhavi 82 Village | 17 | 17 | 0 | 0 | 22 | Functional | 13 | 9 | In Progress
7 | Sangli | Sangli | Islampur | Valva | 7940233 | Peth & two Villages | 3 | 3 | 0 | 0 | 5 | Functional | 0 | 5 | In Progress
8 | Pune | Pune 1 | Baramati | Ambegaon | 7942125 | MURTI & 7 VILLAGES RRWSS | 7 | 7 | 0 | 0 | 13 | Functional | 4 | 9 | In Progress
9 | Pune | Pune 2 | Baramati | Ambegaon | 20018548 | HOL SASTEWADI | 2 | 2 | 0 | 0 | 8 | Functional | 3 | 5 | In Progress

## Pune Datalink (hidden)
| Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | Number of Village | Calc - Village Functional | Calc - Village Partial | Calc - Village Non Functional | Calc - Scheme Status | Number of the Reservoir
\\DemoAF\JJM\JJM\Maharashtra\Region-Pune\Circle-Pune\Division-Pune 2\Sub Division-Pune 2\Block-Velhe\Scheme-20027541-Wangani RRWSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Pune\Circle-Pune\Division-Satara\Sub Division-Phaltan\Block-Phaltan\Scheme-20027892-RR Girvi WSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Pune\Circle-Pune\Division-Pune 1\Sub Division-Baramati\Block-Ambegaon\Scheme-20017250-LONI BHAPKAR RRWSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Pune\Circle-Pune\Division-Pune\Sub Division-Pune\Block-Mulshi\Scheme-20022133 - Peth RR | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Pune\Circle-Pune\Division-Pune 2\Sub Division-Maval\Block-Daund\Scheme-20013367-Done Adhale RR | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Pune\Circle-Sangli\Division-Solapur\Sub Division-Solapur\Block-Sangola\Scheme-20027396 - Alegaon shirbhavi 82 Village | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Pune\Circle-Sangli\Division-Sangli\Sub Division-Islampur\Block-Valva\Scheme-7940233-Peth & two Villages | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Pune\Circle-Pune\Division-Pune 1\Sub Division-Baramati\Block-Ambegaon\Scheme-7942125-MURTI & 7 VILLAGES RRWSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Pune\Circle-Pune\Division-Pune 2\Sub Division-Baramati\Block-Ambegaon\Scheme-20018548-HOL SASTEWADI | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?

## Region - CS Data (hidden)
[16 empty] | 200 | \\WIN-6SIR0BN8BTR\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Buldhana\Sub Division-Buldhana\Block-Buldhana\Scheme-20021406 - Padali & 5 Villages RRWSS\Padli
Region Wise Village Level Progress Report | [15 empty] | 9
30
161
Scheme Level
Sr No. | Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | Number of Village | No. of Functional Village | No. of Partial Village | No. of Non- Functional Village | Total Number of ESR | Scheme Functional Status | No. Fully Completed ESR | Balance ESR | Fully completion Scheme Status
1 | Latur | Latur | Chakur | Chakur | 20030459 | Rachnawadi 6 villages WSS | 2 | 2 | 0 | 0 | 2 | Functional | 2 | 0 | Completed
2 | Chhatrapati Sambhajinagar | Chhatrapati Sambhajinagar | Paithan | Paithan | 20018162 | Paithan Taluka 178 Village Grid WS | 44 | 43 | 0 | 1 | 45 | Partial | 38 | 7 | In Progress
3 | Chhatrapati Sambhajinagar | Chhatrapati Sambhajinagar | Gangapur | Gangapur | 20051233 | 373 Village Gangapur-Vaijapur Grid WSS | 7 | 5 | 0 | 2 | 7 | Partial | 2 | 5 | In Progress
4 | Chhatrapati Sambhajinagar | Chhatrapati Sambhajinagar | Sillod | Sillod | 20017395 | Shirsala & 4 Village | 4 | 3 | 0 | 1 | 5 | Partial | 2 | 3 | In Progress
5 | Nanded | Nanded | Himayatnagar | Himayatnagar | 20013969 | Hadgaon and Himayatnagar 132 Village Grid WSS | 9 | 7 | 1 | 1 | 9 | Partial | 1 | 8 | In Progress
6 | Nanded | Nanded | Naigaon | Naigaon | 7942142 | Manjram WSS (7942142) | 2 | 2 | 0 | 0 | 2 | Functional | 2 | 0 | Completed
7 | Nanded | Parbhani | Senaon | Senaon | 20023330 | Kawtha Bk & 9 Vill RR WSS | 1 | 1 | 0 | 0 | 1 | Functional | 0 | 1 | In Progress
8 | Latur | Latur | Renapur | Renapur | 20030820 | Pangaon 10 villages WSS | 4 | 4 | 0 | 0 | 5 | Functional | 0 | 5 | In Progress
9 | Latur | Latur | Shirur Anantpal | Shirur Anantpal | 20030815 | Sakol 7 villages WSS | 3 | 2 | 1 | 0 | 4 | Partial | 3 | 1 | In Progress
10 | Nanded | Nanded | Kandhar | Kandhar | 7338000 | Osmamnagar Shirdhon Combined WSS | 4 | 4 | 0 | 0 | 7 | Functional | 0 | 7 | In Progress
11 | Nanded | Nanded | Hadgaon | Hadgaon | 20013969 | Hadgaon and Himayatnagar 132 Village Grid WSS | 41 | 33 | 0 | 8 | 41 | Partial | 14 | 27 | In Progress
12 | Chhatrapati Sambhajinagar | Chhatrapati Sambhajinagar | Vaijapur | Vaijapur | 20051233 | 373 Village Gangapur-Vaijapur Grid WSS | 36 | 35 | 0 | 1 | 37 | Partial | 18 | 19 | In Progress

## Nashik Datalink (hidden)
| Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | Number of Village | Calc - Village Functional | Calc - Village Partial | Calc - Village Non Functional | Calc - Scheme Status | Number of the Reservoir
\\DemoAF\JJM\JJM\Maharashtra\Region-Nashik\Circle-Nashik\Division-W M Nashik\Sub Division-W.M.Nashik\Block-Nifad\Scheme-20039258 - Ozar-Sakore & 2 Villages | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nashik\Circle-Nashik\Division-W M Nashik\Sub Division-Sinnar\Block-Naigaon\Scheme-20028193 - Retrofitting To Wadzire (Naigaon) & 4 Villages RRWSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nashik\Circle-Ahmednagar\Division-Sangamner\Sub Division-Sangamner\Block-Sangamner\Scheme-7937337 - Retro.Nimon and 4 villages, Tal. Sangamner | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nashik\Circle-Ahmednagar\Division-Sangamner\Sub Division-Sangamner\Block-Sangamner\Scheme-20033242 - Retro.Talegaon Dighe and 16 villages, Tal. Sangamner | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nashik\Circle-Nashik\Division-W M Nashik\Sub Division-Malegaon\Block-Chandwad\Scheme-20086730 - Retro.Chandwad and WSS 44 villages. Ta. Chandwad | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nashik\Circle-Ahmednagar\Division-Sangamner\Sub Division-Kopargaon\Block-Rahata\Scheme-20054877 - Retro.Kelvad Bk.& 2 villages RRWSS. Ta.Rahta | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nashik\Circle-Ahmednagar\Division-Sangamner\Sub Division-Kopargaon\Block-Rahata\Scheme-417239 - Retro Rui & Shingave R.R.W.S.S Tal Rahata | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nashik\Circle-Jalgaon\Division-Jalgaon\Sub Division-Erandol\Block-Dharangaon\Scheme-20061165 - Paldhi (bk& Kh) RR Tal DHARANGAON | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nashik\Circle-Nashik\Division-W M Nashik\Sub Division-W.M.Nashik\Block-Dindori\Scheme-20039258 - Ozar-Sakore & 2 Villages | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nashik\Circle-Nashik\Division-Nashik\Sub Division-Sinnar\Block-Sinnar\Scheme-20019176 - Retro. Bargaonpimpri & 6 VRWSS Tal Sinnar | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nashik\Circle-Nashik\Division-Nashik\Sub Division-Sinnar\Block-Sinnar\Scheme-20019286 - Nirhale-Fatehpur and 5 villages, Tal. Sinnar | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nashik\Circle-Nashik\Division-Nashik\Sub Division-Manmad\Block-Yeola\Scheme-20030798 - Retrofitting To Yeola 38 Villages | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nashik\Circle-Jalgaon\Division-Jalgaon\Sub Division-Erandol\Block-Chalisgaon\Scheme-20053796 - Dondigar-Rohini & 15 Villages WSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Nashik\Circle-Ahmednagar\Division-Ahmednagar\Sub Division-Newasa\Block-Nevasa\Scheme-5348540 - Retro.Sonai Karjgaon and 16 villages, Tal. Nevasa | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?

## Region - Nashik Data (hidden)
[16 empty] | 200 | \\WIN-6SIR0BN8BTR\JJM\JJM\Maharashtra\Region-Amaravati\Circle-Akola\Division-Buldhana\Sub Division-Buldhana\Block-Buldhana\Scheme-20021406 - Padali & 5 Villages RRWSS\Padli
Region Wise Village Level Progress Report | [15 empty] | 9
30
161
Scheme Level
Sr No. | Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | Number of Village | No. of Functional Village | No. of Partial Village | No. of Non- Functional Village | Total Number of ESR | Scheme Functional Status | No. Fully Completed ESR | Balance to Complete ESR | Fully completion Scheme Status
1 | Nashik | W M Nashik | W.M.Nashik | Nifad | 20039258 | Ozar-Sakore & 2 Villages | 2 | 1 | 1 | 0 | 6 | Partial | 3 | 3 | In Progress
2 | Nashik | W M Nashik | Sinnar | Naigaon | 20028193 | Retrofitting To Wadzire (Naigaon) & 4 Villages RRWSS | 4 | 1 | 1 | 2 | 5 | Partial | 0 | 5 | In Progress
3 | Ahmednagar | Sangamner | Sangamner | Sangamner | 7937337 | Retro.Nimon and 4 villages, Tal. Sangamner | 6 | 2 | 3 | 1 | 19 | Partial | 7 | 12 | In Progress
4 | Ahmednagar | Sangamner | Sangamner | Sangamner | 20033242 | Retro.Talegaon Dighe and 16 villages, Tal. Sangamner | 20 | 3 | 1 | 16 | 50 | Partial | 4 | 46 | In Progress
5 | Nashik | W M Nashik | Malegaon | Chandwad | 20086730 | Retro.Chandwad and WSS 44 villages. Ta. Chandwad | 58 | 16 | 2 | 40 | 75 | Partial | 0 | 75 | In Progress
6 | Ahmednagar | Sangamner | Kopargaon | Rahata | 20054877 | Retro.Kelvad Bk.& 2 villages RRWSS. Ta.Rahta | 3 | 1 | 1 | 1 | 5 | Partial | 0 | 5 | In Progress
7 | Ahmednagar | Sangamner | Kopargaon | Rahata | 417239 | Retro Rui & Shingave R.R.W.S.S Tal Rahata | 2 | 1 | 1 | 0 | 7 | Partial | 4 | 3 | In Progress
8 | Jalgaon | Jalgaon | Erandol | Dharangaon | 20061165 | Paldhi (bk& Kh) RR Tal DHARANGAON | 2 | 1 | 1 | 0 | 6 | Partial | 5 | 1 | In Progress
9 | Nashik | W M Nashik | W.M.Nashik | Dindori | 20039258 | Ozar-Sakore & 2 Villages | 2 | 1 | 1 | 0 | 4 | Partial | 2 | 2 | In Progress
10 | Nashik | Nashik | Sinnar | Sinnar | 20019176 | Retro. Bargaonpimpri & 6 VRWSS Tal Sinnar | 7 | 4 | 1 | 2 | 16 | Partial | 5 | 11 | In Progress
11 | Nashik | Nashik | Sinnar | Sinnar | 20019286 | Nirhale-Fatehpur and 5 villages, Tal. Sinnar | 5 | 2 | 1 | 2 | 11 | Partial | 0 | 11 | In Progress
12 | Nashik | Nashik | Manmad | Yeola | 20030798 | Retrofitting To Yeola 38 Villages | 28 | 17 | 0 | 11 | 33 | Partial | 0 | 33 | In Progress
13 | Jalgaon | Jalgaon | Erandol | Chalisgaon | 20053796 | Dondigar-Rohini & 15 Villages WSS | 17 | 1 | 1 | 15 | 35 | Partial | 0 | 35 | In Progress
14 | Ahmednagar | Ahmednagar | Newasa | Nevasa | 5348540 | Retro.Sonai Karjgaon and 16 villages, Tal. Nevasa | 18 | 3 | 11 | 4 | 36 | Partial | 0 | 36 | In Progress

## CS Datalink (hidden)
| Circle | Division | Sub Division | Block | Scheme ID | Scheme Name | Number of Village | Calc - Village Functional | Calc - Village Partial | Calc - Village Non Functional | Calc - Scheme Status | Number of the Reservoir
\\DemoAF\JJM\JJM\Maharashtra\Region-Chhatrapati Sambhajinagar\Circle-Latur\Division-Latur\Sub Division-Chakur\Block-Chakur\Scheme-20030459 - Rachnawadi 6 villages WSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Chhatrapati Sambhajinagar\Circle-Chhatrapati Sambhajinagar\Division-Chhatrapati Sambhajinagar\Sub Division-Paithan\Block-Paithan\Scheme-20018162 - Paithan Taluka 178 Village Grid WS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Chhatrapati Sambhajinagar\Circle-Chhatrapati Sambhajinagar\Division-Chhatrapati Sambhajinagar\Sub Division-Gangapur\Block-Gangapur\Scheme-20051233 - 373 Village Gangapur-Vaijapur Grid WSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Chhatrapati Sambhajinagar\Circle-Chhatrapati Sambhajinagar\Division-Chhatrapati Sambhajinagar\Sub Division-Sillod\Block-Sillod\Scheme-20017395 - Shirsala & 4 Village RRWS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Chhatrapati Sambhajinagar\Circle-Nanded\Division-Nanded\Sub Division-Himayatnagar\Block-Himayatnagar\Scheme-20013969 - Hadgaon and Himayatnagar 132 Village Grid WSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Chhatrapati Sambhajinagar\Circle-Nanded\Division-Nanded\Sub Division-Naigaon\Block-Naigaon\Scheme-7942142 - Manjram WSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Chhatrapati Sambhajinagar\Circle-Nanded\Division-Parbhani\Sub Division-Senaon\Block-Senaon\Scheme-20023330 -Kawtha Bk & 9 Vill RR WSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Chhatrapati Sambhajinagar\Circle-Latur\Division-Latur\Sub Division-Renapur\Block-Renapur\Scheme-20030820- Pangaon 10 villages WSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Chhatrapati Sambhajinagar\Circle-Latur\Division-Latur\Sub Division-Shirur Anantpal\Block-Shirur Anantpal\Scheme-20030815- Sakol 7 villages WSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Chhatrapati Sambhajinagar\Circle-Nanded\Division-Nanded\Sub Division-Kandhar\Block-Kandhar\Scheme-7338000 - Osmamnagar Shirdhon Combined WSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Chhatrapati Sambhajinagar\Circle-Nanded\Division-Nanded\Sub Division-Hadgaon\Block-Hadgaon\Scheme-20013969 - Hadgaon and Himayatnagar 132 Village Grid WSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
\\DemoAF\JJM\JJM\Maharashtra\Region-Chhatrapati Sambhajinagar\Circle-Chhatrapati Sambhajinagar\Division-Chhatrapati Sambhajinagar\Sub Division-Vaijapur\Block-Vaijapur\Scheme-20051233 - 373 Village Gangapur-Vaijapur Grid WSS | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?